## Slide 1
Welcome to ESoWC!
Migration to Python and GUI for existing calibration software
Mentors: Fatima Pillosu & Tim Hewson
Developer: Anirudha Bose

## Slide 2
Schematic plan for the meetings
(the detailed explanation of the tasks to develop every week will be uploaded the week before in a common source to be defined)
Meetings – At least one per week on Fridays at 3.30 pm

## Slide 3
n. Week | Date Meeting | Tasks for the week | 
1 | 11/05/2018 | Welcome & Task 1 (Creation of the input data database for the calibration software & creation of GUI to read the input data from the database) | 
2 | 18/05/2018 | Delivery and Test of Task 1 | Task 2 (Creation of the module for the computation of the fields - accumulated or instantaneous - for the predictant and predictors, and creation of the relevant part of the GUI)
3 | 25/05/2018 | Delivery and Test of Task 2 | Task 3 (Unit tests and documentation – for software and unit tests - for Tasks 1, 2)
4 | 01/06/2018 | Both mentors not available for telecon (but available via email if there are any questions) | 
5 | 08/06/2018 | Both mentors not available for telecon (but available via email if there are any questions) | 
6 | 15/06/2018 | Both mentors not available | Delivery of Task 3
7 | 22/06/2018 | MILESTONE 1: Completion assessment for Tasks 1, 2, 3 | Task 4
8 | 29/06/2018 | Delivery and Test of Task 4 | Task 5
9 | 06/07/2018 | Delivery and Test of Task 5 | Task 6
10 | 13/07/2018 | Delivery and Test of Task 6 | Task 7 (Unit tests and documentation – for software and unit tests - for Tasks 4, 5, 6)
11 | 20/07/2018 | Delivery and Test of Task 7 | No Task
12 | 27/07/2018 | Developer not available | 
13 | 03/08/2018 | MILESTONE 2: Completion assessment for Tasks 4, 5, 6, 7 | Task 8
14 | 10/08/2018 | Delivery and Test of Task 8 | Task 9
15 | 17/08/2018 | Delivery and Test of Task 9 | Task 10
16 | 24/08/2018 | Delivery and Test of Task 10 | Task 11
17 | 31/08/2018 | Delivery and Test of Task 12 | Task 12 (Unit tests and documentation – for software and unit tests - for Tasks 8, 9, 10, 11)
18 | 07/09/2018 | MILESTONE 3: General revision of the software, the GUI, the unit tests, and the documentation. Final comments. | 
19 | 14/09/2018 | MILESTONE 4: Assessment about the completion of the whole challenge. Delivery of the final version of the software, the GUI, the unit tests, and the documentation | 

## Slide 4
Requirements to considered the challenge completed

## Slide 5
The progress made by the developer will be assessed at every milestone (see calendar).
    The tested tasks will be considered completed if the mentors can test them successfully, and the unit tests and the software are well documented.
    Documentation and unit tests are considered part of the challenge! So if the unit tests and the software are not well documented the tasks won’t be considered completed.
    For “software documentation” is intended comments inside the code to allow an easy future development of the software, and manual for users with examples to allow an easy usage of the software.
The whole challenge will be considered successfully completed only if all milestones are considered completed.

## Slide 6
Task 1
Creation of the database that contains the input data for the calibration software
Creation of the part of the GUI that read the input data

## Slide 7
Content of Task1
Creation of the database that contains the input data for the calibration software
(upgraded, look at the notes attached to the email)
Structure of the database
/vol/ecpoint/ecPoint_DB/Forecasts/[origin]/[predictant & predictors]/[date-time]/
/vol/ecpoint/ecPoint_DB/Observations/[predictant]/[type]/[date]/
Name of the files
Forecasts: [variable]_[date]_[time]_[step]
Observations: [variable]_[type]_[date]_[end-of-period]
The structure of the database is IMPORTANT because it will be interrogated by the calibration software.
What could be the best way to create this structure with no errors?
(e.g. a file that will create the structure of the database and the user will populate the directories?)

## Slide 8
Content of Task1
Creation of the part of the GUI that read the input data
The GUI needs to read the following data
  Types of forecasts to read
Minimum required: grib (eccodes needed), netCDF, ascii (csv)
  Types of observations to read
Minimum required: geopoints, ascii (csv)